## Bugs Report
|  | Project Name |  |  | Defect Identified | Defects Closed | Pending Defects
|  | RBT Kentico Support |  |  | 76 | 64 | 12
S. No | Environment | Hive Ticket ID | Status |  | Issue | Status | Start Date | End date | Assignee
1 |  | #262607 | done |  | Auto responder and email notification | Closed | 2022-11-29 | 2022-12-21 | Akhilbabu Kothuri
2 | QA | #262609 |  |  | Image loading issue in Case Study page. | In progress | 2022-11-30 |  | Akhilbabu Kothuri
3 |  | #262613 | done |  | Videos not displayed in Leadership Team page | Closed | 2022-11-30 | 2022-12-21 | Akhilbabu Kothuri
4 | live | #262678 |  |  | In DIGITAL TRANSFORMATION ADOPTION & STAGES page proper information is not displaying. | New | 2022-12-06 |  | Akhilbabu Kothuri
5 | live | #262659 |  | UI | Incorrect image alignment in Microsoft Dynamics CRM page | New | 2022-12-05 |  | Venkata Raguru
6 | live | #262656 |  | UI | Incorrect alignment in IBM Cognos Analytics page | New | 2022-12-05 |  | Venkata Raguru
7 | live | #262650 |  |  | In contact page incorrect contact information in India | New | 2022-12-05 |  | Akhilbabu Kothuri
8 | QA | #262629 | Done | UI | Empty blocks Created in RESOURCES, PRIVACY POLICY, TERMS OF USE pages | New | 2022-12-01 |  | Venkata Raguru
9 | QA | #262624 |  |  | 404 Error for contact page | New | 2022-12-01 |  | Akhilbabu Kothuri
10 | QA | #262621 | Done | UI | Incorrect alignment for images in CSR page | New | 2022-11-30 |  | Akhilbabu Kothuri
11 | QA | #262620 | Done | UI | Extra block created in clients page | New | 2022-11-30 |  | Akhilbabu Kothuri
12 | QA | #262619 | Done |  | Incorrect functionality in Home page. | New | 2022-11-30 |  | Akhilbabu Kothuri
13 |  | #262684 | Done | UI | Incorrect alignment in Power BI page | Closed | 2022-12-06 | 2022-12-26 | Venkata Raguru
14 |  | #262685 | Done | UI | Incorrect alignment in SharePoint Portal page. | Closed | 2022-12-06 | 2022-12-26 | Venkata Raguru
15 |  | #262687 | Done |  | Email sharing is not working in blog template when we click on email icon | Closed | 2022-12-06 | 2022-12-27 | Akhilbabu Kothuri
16 |  | #262695 | Done |  | Merry Christmas -Home Page Modal Pop Up and LP | New | 2022-12-06 |  | Akhilbabu Kothuri
17 | QA | #262753 | Done |  | Extra block created in Microsoft Dynamics 365. | New | 2022-12-13 |  | Venkata Raguru
18 | QA | #262754 |  |  | Incorrect functionality in Microsoft Dynamics AX page. | New | 2022-12-13 |  | Venkatarao Boosa
19 | QA | #262756 |  |  | Incorrect dropdown icons in Microsoft Dynamics NAV page. | New | 2022-12-13 |  | Venkatarao Boosa
20 | QA | #262758 | Done | UI | Extra block created in ERP Architecture Planning page. | New | 2022-12-13 |  | Venkatarao Boosa
21 | QA | #262759 | Done | UI | Extra block created in ERP Support Services page | New | 2022-12-13 |  | Venkatarao Boosa
22 | QA | #262760 | Done | UI | Extra block created in ERP Testing and Validation page. | New | 2022-12-13 |  | Venkatarao Boosa
23 | QA | #262763 | Done | UI | Extra block created in Customer Relationship Management page | New | 2022-12-13 |  | Venkata Raguru
24 |  | #262779 | Done | UI | Incorrect alignment in Drupal CMS Solutions page. | Closed | 2022-12-14 | 2022-12-26 | Venkatarao Boosa
25 | live | #262780 | Done | UI | Incorrect alignment in SITECORE CMS page. | New | 2022-12-14 |  | Venkatarao Boosa
26 |  | #262782 | Done |  | 404 Error found for Liferay Portal Solutions page | Closed | 2022-12-14 | 2022-12-30 | Venkatarao Boosa
27 |  | #262818 | Done |  | Incorrect Information for Cab Facility benefit | Closed | 2022-12-16 | 2022-12-30 | Venkatarao Boosa
28 |  | #262819 | Done |  | Incorrect information for Communication Skills Training in Life at Ray Business Technologies page | Closed | 2022-12-16 | 2022-12-30 | Venkatarao Boosa
29 | live | #262820 |  |  | Incorrect functionality for images in Life at Ray Business Technologies page | New | 2022-12-16 |  | Venkatarao Boosa
30 | live | #262821 | Done |  | Videos unavailable in RAY BUSINESS TECHNOLOGIE'S EMPLOYEE TESTIMONIALS | New | 2022-12-16 |  | Venkatarao Boosa
31 | live | #262835 |  |  | Clicking function is not working in contact page. | New | 2022-12-19 |  | Venkatarao Boosa
32 | live | #262833 | Done |  | search function is not working properly in Careers page | New | 2022-12-19 |  | Venkatarao Boosa
32 | live | #262854 | Done |  | Image loading issue and getting page error for an article of Raybiztech re-branded leading IT Company in News-Events page. | New | 2022-12-20 |  | Akhilbabu Kothuri
33 |  | #262849 | Done | UI | Incorrect alignment in Magento Development Services page | Closed | 2022-12-20 | 2022-12-27 | Akhilbabu Kothuri
34 | live | #262843 |  |  | Incorrect data for Canada address in contact page. | New | 2022-12-20 |  | Akhilbabu Kothuri
35 | live | #262859 | Done |  | RBT Blogs-Duplicate Blog Articles | Closed | 2022-12-21 | 2023-01-10 | Akhilbabu Kothuri
36 | live | #262867 | Done | UI | Incorrect alignment in Xamarin Mobile Apps Development page | New | 2022-12-21 |  | Akhilbabu Kothuri
37 | live | #262902 | Done |  | 404 Error found in while clicking on vTiger CRM Solutionssection in Customer Relationship Management page | New | 2022-12-26 |  | Akhilbabu Kothuri
38 | live | #262944 | Done |  | Getting incorrect information when I click on Forecasting section in Artificial Intelligence page. | New | 2022-12-28 |  | Akhilbabu Kothuri
39 | QA | #262946 | Done |  | 404 Error found in while clicking on CASE STUDIES in Hemberger menu | New | 2022-12-28 |  | Akhilbabu Kothuri
40 | live | #262947 |  |  | widgets missing RHS | New | 2022-12-30 |  | Akhilbabu Kothuri
41 | live | #262986 |  | UI | Alignment issues Cogonos landing page | New | 2023-01-12 |  | Akhilbabu Kothuri
42 | live | #262990 |  |  | Menu UI Issues | New | 2023-01-16 |  | Akhilbabu Kothuri
[6 empty] | 16 | 5
27

## Sheet2
Project Name | Defect Identified | Defects Closed | Pending Defects
RBT Kentico Support | 76 | 64 | 12

## Pending Bugs
S. No | Environment | Hive Ticket ID | Status | Issue | Status | Start Date | End date | Assignee
2 | QA | #262609 | done | Image loading issue in Case Study page. | In progress | 2022-11-30 |  | Akhilbabu Kothuri
4 | live | #262678 |  | In DIGITAL TRANSFORMATION ADOPTION & STAGES page proper information is not displaying. | New | 2022-12-06 |  | Akhilbabu Kothuri
5 | live | #262659 |  | Incorrect image alignment in Microsoft Dynamics CRM page | New | 2022-12-05 |  | Venkata Raguru
7 | live | #262650 |  | In contact page incorrect contact information in India | New | 2022-12-05 |  | Akhilbabu Kothuri
9 | QA | #262624 |  | 404 Error for contact page | New | 2022-12-01 |  | Akhilbabu Kothuri
18 | QA | #262754 |  | Incorrect functionality in Microsoft Dynamics AX page. | New | 2022-12-13 |  | Venkatarao Boosa
19 | QA | #262756 |  | Incorrect dropdown icons in Microsoft Dynamics NAV page. | New | 2022-12-13 |  | Venkatarao Boosa
29 | live | #262820 |  | Incorrect functionality for images in Life at Ray Business Technologies page | New | 2022-12-16 |  | Venkatarao Boosa
31 | live | #262835 |  | Clicking function is not working in contact page. | New | 2022-12-19 |  | Venkatarao Boosa
34 | live | #262843 |  | Incorrect data for Canada address in contact page. | New | 2022-12-20 |  | Akhilbabu Kothuri
40 | live | #262947 | done | widgets missing RHS | New | 2022-12-30 |  | Akhilbabu Kothuri
41 | live | #262986 | done | Alignment issues Cogonos landing page | New | 2023-01-12 |  | Akhilbabu Kothuri
42 | live | #262990 |  | Menu UI Issues | New | 2023-01-16 |  | Akhilbabu Kothuri

## Closed bugs
S. No | Environment | Hive Ticket ID | Status | Issue | Status | Start Date | End date | Assignee
1 |  | #262607 | done | Auto responder and email notification | Closed | 2022-11-29 | 2022-12-21 | Akhilbabu Kothuri
3 |  | #262613 | done | Videos not displayed in Leadership Team page | Closed | 2022-11-30 | 2022-12-21 | Akhilbabu Kothuri
6 | live | #262656 | Done | Incorrect alignment in IBM Cognos Analytics page | New | 2022-12-05 |  | Venkata Raguru
8 | QA | #262629 | Done | Empty blocks Created in RESOURCES, PRIVACY POLICY, TERMS OF USE pages | New | 2022-12-01 |  | Venkata Raguru
10 | QA | #262621 | Done | Incorrect alignment for images in CSR page | New | 2022-11-30 |  | Akhilbabu Kothuri
11 | QA | #262620 | Done | Extra block created in clients page | New | 2022-11-30 |  | Akhilbabu Kothuri
12 | QA | #262619 | Done | Incorrect functionality in Home page. | New | 2022-11-30 |  | Akhilbabu Kothuri
13 |  | #262684 | Done | Incorrect alignment in Power BI page | Closed | 2022-12-06 | 2022-12-26 | Venkata Raguru
14 |  | #262685 | Done | Incorrect alignment in SharePoint Portal page. | Closed | 2022-12-06 | 2022-12-26 | Venkata Raguru
15 |  | #262687 | Done | Email sharing is not working in blog template when we click on email icon | Closed | 2022-12-06 | 2022-12-27 | Akhilbabu Kothuri
16 |  | #262695 | Done | Merry Christmas -Home Page Modal Pop Up and LP | New | 2022-12-06 |  | Akhilbabu Kothuri
17 | QA | #262753 | Done | Extra block created in Microsoft Dynamics 365. | New | 2022-12-13 |  | Venkata Raguru
20 | QA | #262758 | Done | Extra block created in ERP Architecture Planning page. | New | 2022-12-13 |  | Venkatarao Boosa
21 | QA | #262759 | Done | Extra block created in ERP Support Services page | New | 2022-12-13 |  | Venkatarao Boosa
22 | QA | #262760 | Done | Extra block created in ERP Testing and Validation page. | New | 2022-12-13 |  | Venkatarao Boosa
23 | QA | #262763 | Done | Extra block created in Customer Relationship Management page | New | 2022-12-13 |  | Venkata Raguru
24 |  | #262779 | Done | Incorrect alignment in Drupal CMS Solutions page. | Closed | 2022-12-14 | 2022-12-26 | Venkatarao Boosa
25 | live | #262780 | Done | Incorrect alignment in SITECORE CMS page. | New | 2022-12-14 |  | Venkatarao Boosa
26 |  | #262782 | Done | 404 Error found for Liferay Portal Solutions page | Closed | 2022-12-14 | 2022-12-30 | Venkatarao Boosa
27 |  | #262818 | Done | Incorrect Information for Cab Facility benefit | Closed | 2022-12-16 | 2022-12-30 | Venkatarao Boosa
28 |  | #262819 | Done | Incorrect information for Communication Skills Training in Life at Ray Business Technologies page | Closed | 2022-12-16 | 2022-12-30 | Venkatarao Boosa
30 | live | #262821 | Done | Videos unavailable in RAY BUSINESS TECHNOLOGIE'S EMPLOYEE TESTIMONIALS | New | 2022-12-16 |  | Venkatarao Boosa
32 | live | #262833 | Done | search function is not working properly in Careers page | New | 2022-12-19 |  | Venkatarao Boosa
32 | live | #262854 | Done | Image loading issue and getting page error for an article of Raybiztech re-branded leading IT Company in News-Events page. | New | 2022-12-20 |  | Akhilbabu Kothuri
33 |  | #262849 | Done | Incorrect alignment in Magento Development Services page | Closed | 2022-12-20 | 2022-12-27 | Akhilbabu Kothuri
35 | live | #262859 | Done | RBT Blogs-Duplicate Blog Articles | Closed | 2022-12-21 | 2023-01-10 | Akhilbabu Kothuri
36 | live | #262867 | Done | Incorrect alignment in Xamarin Mobile Apps Development page | New | 2022-12-21 |  | Akhilbabu Kothuri
37 | live | #262902 | Done | 404 Error found in while clicking on vTiger CRM Solutionssection in Customer Relationship Management page | New | 2022-12-26 |  | Akhilbabu Kothuri
38 | live | #262944 | Done | Getting incorrect information when I click on Forecasting section in Artificial Intelligence page. | New | 2022-12-28 |  | Akhilbabu Kothuri
39 | QA | #262946 | Done | 404 Error found in while clicking on CASE STUDIES in Hemberger menu | New | 2022-12-28 |  | Akhilbabu Kothuri

## Sheet1
262678
262659
262656
262624
262754
262756
262820
262833
262843
262986
262990